## Sheet1
Flash
| Item | Progress | Comment
ECM | Check ECM part number
Record Calibration part number
VIN to be programmed
ESN to be programmed
Vehicle speed value revised based on GVW and Tire size
Speed limit to be cleared
DCU | Check DCU part number
Record Calibration part number
VIN to be programmed
MIMAMORI | Installed ECU data
Engine model data
Transmission model data
Tire radius data
Final ratio data
Vehicle type data
Electrical compornent data
Final drive gear ratio data
Vehicle speed correction coefficient
New mimamori calibration data
Deterioration of Engine Oil
Starter life
Exhaust valve OH
ACG OH
Transmission OH
Test
| Item | Progress | Comment
Front Axle | Brake force test
ABS Test
Rear Axle | Speed meter test
MAF learning
| Brake force test |  | Done
| ABS Test |  | Moved from a high speed ABS test to a low speed ABS test, currently debugging
Inspection
| Item | Progress | Comment
AT inspection
TCM inspection | Check DTC |  | Ran into issues with unsupported service IDs
Clear DTC
ECM inspection | Check Vin number
DPD switch inspection
Differential pressure sensor check
| Idling parameter inspection |  | Attempted, but most of the tests failed, needs to be debugged, originally was halted due to ECM issue
Check DTC
Clear DTC
MEC Lock
DCU inspection | Check DTC |  | Attempted, but the response handling needs to be debugged
| Clear DTC |  | done
MEC Lock
Mimamori inspection | Total mileage
Fuel economy
Data record memory engine,AT,SCR
EDR,AT Oil temperature
Check DTC
Clear DTC
Clear history
MEC Lock