## Sheet1
Number | Level of interest | Item | Extra conditions | More info | BEP Notes | BEP Hours
1 | Want | Separate Burnish test | a. See example reports b. In same file as Brake Test, but new hierarchy c. Only send burnish result if it was ran | We want to Factory-gate-interlock on burnish. Currently, if a car is retested without running burnish then MES will show Burnish fail, but overall pass | Only send burnish results to MES if burnish test was performed. | 4
2 | Considering | Calculate energy during burnish | a. See example reports b. Want 1 number for each corner, units of MJ*kW c. Result calculated as: sum of C*(Vi^2-Vf^2)^3/ABS(Vi^2-Vf^2) where: 1. C is a configurable constant (1 per wheel) used for unit converstion 2. Vi is initial speed (i.e. speed from previous sample) 3. Vf is final speed (i.e. speed of current sample) 4. Only add to sum if brake switch is detected on a. If not possible, use force/speed triggers (like BaseBrake) 1. Start force = 100 lbf (configurable) 2. End speed = 25 mph (configurable) | In the future we may use this number for pass/fail or to control number of burnish iterations (i.e only move on to brake test once an energy accumulation threshold has been reached) | Analyze each ICM sample from Brake Switch on to ending speed. | 8
3 | Considering | Reactive number of burnish iterations | a. This would be in addition to #2 b. After 6 Burnish stops, display to operator "Need 1 more Burnish stop" and require a 7th iteration. Repeat until all 4 corner's burnish setoint are reached or 11 iterations are complete, whichever comes first. 1. Min (here 6) and Max (here 11) number of Burnish stops configurable 2. Minimun burnish amount = 2000 MJ*kW (configurable) 3. Report Pass/Fail/Abort for each corner individually 4. Overall burnish result dependent on individual corners |  | This is dependent on item 2 above | 4
4 | Want | Add cycletime counters | a. Applies to Burnish and Brake tests b. Measured from start to end of particular test, not vehicle present c. See example reports |  | Add separate cycle time counters for Burnish test and Brake test. Brake test is everything after Burnish test. | 6
5 | Need | Read VIN from CAN | a. With ability to override via barcode scan or from computer |  |  | 8
6 | Need | Multiple test configurations | a. Preferred method is: automatically read VIN from CAN, ask MES for Option Codes via webservice, choose test type 2. Open to other options if this isn’t possible, such as reading vehicle configuration info from CAN b. Desired target/min/max parameters to vary include: Burnish iterations and displayed force target, drag, build, reduction, front balance, rear balance, front-to-rear balance, base brake force and displayed force target, C constants of burnish energy calculation. c. Want ability to override VIN or type, or revert to current method d. Report type to MES | ZTS is done at NCA using a webservice to read option codes from MES | Integrate web service from NCA group to pull option codes from MES | 80
7 | Want | Display remaining burnish stops to operator |  | Operators sometimes brake or accelerate during drag test |  | 4
8 | Need | Use minimum drag limit | a. Add minimum limit (configurable) | Operators sometimes accelerate/brake during drag test, this way at least test will fail (for drag) if they do, instead of giving bad values. Could also use brake/accelerator pedal monitoring to detect, then fail test and display message to operator (next item) |  | 2
9 | Considering | Pedal monitoring during drag |  |  | Read brake pedal switch to verify it is off during the drag test. Software should wait for brake switch off before starting drag measurement. | 4
10 | Need | Report Generator immediate processing |  | Currently batch processing every 5 minutes unless operator clicks Check For Data | Update timer interval in code to 1 second | 1
11 | Need | Send all test results to MES | a. Still want ability to retest without releasing vehicle or rescanning | Currently operators can retest and the initial failure is not reported. Don't want to simply remove retest option because it will take longer to restart test and reinitialize car | Remove in-cycle retest, but allow the test to restart without releasing or rescanning the vehicle. Enable test component reuse. Pre-launch components similar to Chrysler. | 40
12 | Need | Remove brakeprogramvin | a. Includes test, pass/fall criteria, MES report, printout |  |  | 1
13 | Need | Remove modulepartnumber and partnumberparameter | a. Includes test, pass/fall criteria, MES report, printout |  |  | 1
14 | Need | Help troubleshoot data abnormalities | a. See screenshots showing observed data problems. I can send result and log files | Noticed spikes in force/speed data, and missing labels | Reviewed graphs with Jacob. See some spikes in data. Suggested he check motor cable routing and encoder cable routing. Also suggested swapping encoders to see if problem follows. | 0
15 | Need | Help troubleshoot network problems |  | Mapped drives lose connection, linux Lane 1 is worst, then Lane 2. Lane 3 rarely has problems | Suggested using FileZilla for accessing files between Windows and QNX | 0
16 | Considering | Change Build calculation | a. Use average of all samples in a configurable window. Window to have configurable duration and delay since valve is commanded open. Delay and duration configurable (parameter can be number of samples or time, either works) b. Want option to use average (proposed) or peak (current method) |  | Tesla considering using average value for ABS recovery calculation instead of max force value. On hold for now until get feedback from Tesla Engineering on advantage of this approach | 0
17 | Considering | Simulated inertia / added force using RB motors |  | Physical machine interial is 1/3 that of vehicle on road. Requires more burnish iterations than it would on road | Feasible, but would need 2 extra motor drives so as not to extend the test cycle time. On hold for now until Tesla decides if this is really needed. | 0